## Product Backlog
Product Name: | Robbie Robot Shop
Team ID:
Name: | Kevin Childs
Initials: | KRC
Student ID: | 1001298271
(Additional names for teams only)
Name: | Alexis Nunez
Initials: | AN
Student ID: | 1000919601
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Total Features | 11
Sprint 1 Left | 11
Sprint 2 Left | 6
Sprint 3 Left | 1
Sprint 4 Left | 1
Sprint 5 Left | 1
Sprint 6 Left | 1
Sprint 7 Left | 1
Sprint 8 Left | 0
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Sprint # | As a... | I want to... | So that... | Notes
KC | 1 | completed | 2 | PM | create robot parts | I can define robot models | No menu required here – run program, create a part
KC | 2 | completed | 2 | PM | define new robot models | RRS can sell them to our Beloved Customers | Menu needed – create parts, then create a robot model
AN | 3 | completed | 2 | BC | browse a catalog of robots | I can buy one or more robots | Need to list robots models, then list parts in selected model
KC | 4 | completed | 3 | SA | create a robot order for a Customer | I can sell robots and thus do my job well | Select robot model and quantity, show details with total price
AN | 5 | completed | 3 | PB / SA | view a list of orders per SA | I can estimate the value of employees / I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
AN | 6 | completed | 2 | BC | view my orders | see what I have coming to me | Show list of orders for a BC with total price, then list details of selected order
AN | 7 | completed | 2 | BC | view my bill | I can pay for my robots | Show a BC invoice. Actual payment is outside the scope of this project
AN | 8 | completed | 3 | SA | view a sales report | I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
AN/KC | 9 | completed | 3 | PB | view a list of orders | I can manage the company | Show list of every order with total price, then list details of selected order
KC | 10 | completed | 3 | PM | delete robot parts | obsolete parts aren't accidentally used | Delete Robot parts and don't allow adding them to new robot models
KC | 11 | completed | 3 | PM | delete robot models | obsolete robots aren't ordered | Delete Robot models and don't allow adding them to new orders
AN/KC | 12 | completed | 8 | PM | completely convert from CLI to GUI | The user has a better experience | no command line

## Sprint1 Backlog
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 3
Day 1 Left | 3
Day 2 Left | 3
Day 3 Left | 3
Day 4 Left | 2
Day 5 Left | 2
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | UML | RP | Model | KC | Create Use Case Diagram | Complete
2 | UML | RP | Model | AN | Create Class Diagram | Complete
3 | Git | RP | code | KC and AN | Set up Git Hub | Complete

## Sprint2 Backlog (2)
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 6
Day 1 Left | 6
Day 2 Left | 5
Day 3 Left | 4
Day 4 Left | 3
Day 5 Left | 2
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | code | RP | code | KC | Create Robot Parts Classes | Complete
2 | code | RP | code | KC | Create Menu | Complete
3 | code | RP | code | KC | Create Product Manager Class | Complete
4 | code | RP | code | AN | Create Beloved customer class | Complete
5 | code | RP | code | AN | Test Beloved Customer features | Complete
6 | excel | RP | backlog | AN | Update sprint 2 Backlog | Complete

## Sprint3 Backlog
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 7
Day 1 Left | 7
Day 2 Left | 6
Day 3 Left | 5
Day 4 Left | 4
Day 5 Left | 2
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | code | RP | code | AN | Create Boss Class | Complete
2 | code | RP | code | AN | Create Sales Associate | Complete
3 | code | RP | code | KC | Test Product Manager Features | Complete
4 | code | RP | code | KC | Test Boss features | complete
5 | code | RP | code | KC | Test Sales Associate Features | complete
6 | excel | RP | backlog | AN/KC | Test the entire program | complete
7 | excel | RP | backlog | AN/KC | update sprint 3 UML and Backlog | complete

## Sprint4 Backlog
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 1
Day 1 Left | 1
Day 2 Left | 1
Day 3 Left | 1
Day 4 Left | 1
Day 5 Left | 1
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | exam | RP | exam | AN | Study for Exam | Complete

## Sprint5 Backlog
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 3
Day 1 Left | 3
Day 2 Left | 3
Day 3 Left | 2
Day 4 Left | 2
Day 5 Left | 1
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | code | RP | code | AN/KC | Install FLTK | Complete
2 | code | RP | code | KC | Create Window with widgets | Complete
3 | code | RP | code | AN | Test Window with widgets | Complete

## Sprint6
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 4
Day 1 Left | 4
Day 2 Left | 3
Day 3 Left | 2
Day 4 Left | 2
Day 5 Left | 1
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | code | RP | code | AN | create gui menu for customer | Complete
2 | code | RP | code | KC | create gui menu for sales associate | Complete
3 | code | RP | code | KC | create gui menu for product manager | Complete
4 | CODE | RP | CODE | AN | create gui menu for boss | complete

## Sprint7
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 4
Day 1 Left | 3
Day 2 Left | 3
Day 3 Left | 2
Day 4 Left | 1
Day 5 Left | 1
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | code | RP | code | AN | create gui menu for creating customer | Complete
2 | code | RP | code | KC | create gui menu for creating sales associate | Complete
3 | code | RP | code | KC | create gui menu for creating robot part | Complete
4 | CODE | RP | CODE | AN | create gui menu for creating robot model | complete
5 | CODE | RP | CODE | AN | integrate files to GUI customer | complete
6 | CODE | RP | CODE | KC | integrate files to GUI sales associate | complete

## Sprint8
Sprint # | 1
Start on | 2016-09-29
End on | 2016-10-06
Demo on | 2016-10-06
Total Tasks | 4
Day 1 Left | 4
Day 2 Left | 3
Day 3 Left | 3
Day 4 Left | 2
Day 5 Left | 2
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | code | RP | code | AN/KC | Debug GUI | Complete
2 | code | RP | code | KC | Test GUI | Complete
3 | UML | RP | UML | AN/KC | complete GUI UML diagrams | Complete
4 | Excel | RP | scrum | AN | Update Excel Sheet | complete